## 工作表1
Joyance - 2023
No | Question: | Comments: | Corrective Action | Responsible Person | Completion Date | Target Completion Date | Supporting | DSI Comment
2 | Aisles and doorways clear of obstructions: | EAs observed that most the escape routes were free of obstruction, except for the cutting and buttoning sections which were partially blocked by the roles of fabric and the pills of unfinished products that was not enough for two way traffics in case of emergency. | The factory will set up more additional emergency exits for problem section. The factory will call manager of all teams in all departments to teach more about OSH | Mr. Lim Phengnara | 2023-06-21 | 2023-06-30 |  | Blocked passages - inform cutting supervisor to clear those blockage. Take photos (1 day) Adding with training and monitoring record (1 day which suppose has a template)
18 | Factory performs legally required number of fire drills: | Based on documents provided for EAs reviews and it confirmed that management did not conduct the emergency drills for all workers every 6 months. The last two emergency drills were held on April 4, 2022 and on October 3, 2022. However, the employer failed to conduct the emergency drill in 2023 because it was over 6 months up to this assessment visit. The employer should conduct emergency drills once every six months and make sure that workers should know how to react in case of an emergency. On May 12, 2023, the employer provided the minutes of new emergency drill which was conducted to all workers on April 29, 2023. However, EAs considered that this issue had just been improved after our visited and EAs will follow-up on this issue by the next assessment visit. | The factory promises that there will be no more deadlines for emergency drill training, and the factory plans for the next training on 07 Oct 2023 | Mr. Lim Phengnara | 2023-10-07 | 2023-10-30 |  | Arrange fire drill within 1 day with record. Factory should have a list of all training schedule in calendar (pls provide a master record)!!!